# WEEKLY PROJECT REPORT

Date: 13th Mar, 2021

Name: Jaydeep Dinesh Dhurat

Prn: 2018016401691167

Roll No: 12																   Batch: B1        															 Project Guide: Prof. Ankita Shah												 Project Name: Ultrasonic Navigation System for Blind People

Synopsis :

In our life we meet many disable people, some of them are partially and some are completely disable. The partially impaired people like dumb, and blind manages their life with difficulties and feel separated from others.

Therefore, communication plays a major role and make them feel better and help them to indulge in an activity where they can see themselves as an independent person in public areas.

This will help them in setting up correspondence between Blind/Dumb and the outside world.

The meeting with the guide started on at 8:30 am end at 8:45 am. During the meeting, I explained my project through presentation/pdf along with analysis. The description of the proposed system is as follows:

- By wearing this device they can fully avoid the use of white cane and such other devices.

- This device will help the blind to navigate without holding a stick which is a bit annoying for them.

- They can simply wear it as a band or cloth and it can function very accurately.

- Blind individuals only need a very little training to use it.

- This system is equipped with ultrasonic sensor, according to ease of individual we can make many modules which are connected to the different parts of the body.

- When the ultrasonic sensor detects obstacle the system will notify the individual through vibrations.

- intensity of vibration and sound can be adjustable.

SUGGESTION FROM GUIDE:  This is the weekly report of project session held on 13th Mar, 2021 Till the date I bought my raspberry-pi 3 B + module and ultrasonic sensor, vibrating coin motor, buzzer and LED. With all these components made an integrated circuit on to raspberry-pi 3 B + and tested all the actuator and sensors individually to check whether it’s working fine or not. In this session i haven’t presented any demo video of project or pdf though the project working is as same as the demo video which is presented & explained to the guide last time. Concerned guide has also suggested me to check whether the device is detecting water surface or not. on that i have checked and found that the device is absolutely detecting water but only if the flow is continuous and not discrete.in the span of last two weeks, I worked on the coding part of the project where I have to implement the distance and beeping logic of buzzer according to range of device. Guide has also asked me to attach some images of circuit which is shown below.

Thank You!

Progress Report of the Project

|  | Review Date | Percent Complete [Student] | Percent Complete [Guide] |
| --- | --- | --- | --- |
| 1 | Saturday, February 6, 2021 | 3 % | 2 % |
| 2 | Saturday, February 13, 2021 | 7 % | 5 % |
| 3 | Saturday, February 20, 2021 | 10 % | 6 % |
| 4 | Saturday, February 27, 2021 | 13 % |  |
| 5 | Saturday, March 6, 2021 | 20 % |  |
| 6 | Saturday, March 13, 2021 | 35 % |  |
| 7 | Saturday, March 20, 2021 |  |  |
| 8 | Saturday, March 27, 2021 |  |  |

Potential timeline of the Project’s Progress

|  | Task Name | Planned Start Date | Planned Finish Date | Planned Duration (in days) | Actual Start Date | Actual Finish Date | Signature of the Guide |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Analysis | Monday, February 1, 2021 | Wednesday, February 10, 2021 | 8 | 1st Feb, 2021 | 10th Feb, 2021 |  |
| 1.1 | Defining Problem Statement of the Project and gathering Information | Monday, February 1, 2021 | Thursday, February 4, 2021 | 4 | 2nd Feb, 2021 | 4th Feb, 2021 |  |
| 1.2 | Document Current System | Tuesday, February 9, 2021 | Wednesday, February 10, 2021 | 2 | 5th Feb, 2021 | 7th Feb, 2021 |  |
| 1.3 | Analysis Complete | Wednesday, February 10, 2021 | Wednesday, February 10, 2021 | 0 | 10th Feb, 2021 | 10th Feb, 2021 |  |
| 2 | Design | Thursday, February 11, 2021 | Thursday, March 4, 2021 | 16 | 11th Feb, 2021 | 4th March, 2021 |  |
| 2.1 | Design Database | Thursday, February 11, 2021 | Tuesday, February 16, 2021 | 4 | 11th Feb, 2021 | 13th Feb, 2021 |  |
| 2.2 | Software Design | Wednesday, February 17, 2021 | Wednesday, February 24, 2021 | 5 | 17th Feb, 2021 | 20th Feb, 2021 |  |

|  | Task Name | Planned Start Date | Planned Finish Date | Planned Duration (in days) | Actual Start Date | Actual Finish Date | Signature of the Guide |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2.3 | Interface Design | Wednesday, February 24, 2021 | Thursday, February 25, 2021 | 2 | 21st Feb, 2021 | 22nd Feb, 2021 |  |
| 2.4 | Create Design Specification | Friday, February 26, 2021 | Thursday, March 4, 2021 | 5 | 24th Feb, 2021 | 1st Mar, 2021 |  |
| 2.5 | Design Complete | Thursday, March 4, 2021 | Thursday, March 4, 2021 | 0 | 4th March, 2021 | 4th Mar, 2021 |  |
| 3 | Development | Thursday, February 11, 2021 | Monday, March 15, 2021 | 21 | 11th Feb, 2021 | 15th Mar, 2021 |  |
| 3.1 | Develop System Module | Thursday, February 11, 2021 | Friday, February 26, 2021 | 11 | 11th Feb, 2021 | 21st Feb, 2021 |  |
| 3.2 | Integrate System Module | Monday, March 1, 2021 | Tuesday, March 9, 2021 | 7 | 1st Mar, 2021 | 6th Mar, 2021 |  |
| 3.3 | Perform Initial Testing | Wednesday, March 10, 2021 | Monday, March 15, 2021 | 3 | 10th Mar, 2021 | 14th Mar, 2021 |  |
| 3.4 | Development Complete | Monday, March 15, 2021 | Monday, March 15, 2021 | 0 | 15th Mar, 2021 | 15th Mar, 2021 |  |
| 4 | Testing | Monday, March 1, 2021 | Thursday, March 25, 2021 | 17 | 1st Mar, 2021 | 25th Mar, 2021 |  |

|  | Task Name | Planned Start Date | Planned Finish Date | Planned Duration (in days) | Actual Start Date | Actual Finish Date | Signature of the Guide |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 4.1 | Perform System Testing | Monday, March 1, 2021 | Wednesday, March 10, 2021 | 8 |  |  |  |
| 4.2 | Documenting Issues Found | Friday, March 12, 2021 | Friday, March 19, 2021 | 6 |  |  |  |
| 4.3 | Correcting/Resolving Issues Found | Monday, March 22, 2021 | Wednesday, March 24, 2021 | 3 |  |  |  |
| 4.4 | Testing Complete | Wednesday, March 24, 2021 | Wednesday, March 24, 2021 | 0 |  |  |  |
| 5 | Implementation | Thursday, March 25, 2021 | Tuesday, March 30, 2021 | 4 |  |  |  |
| 5.1 | On-Site/On-Campus Installation | Thursday, March 25, 2021 | Monday, March 29, 2021 | 3 |  |  |  |
| 5.2 | Demonstration | Tuesday, March 30, 2021 | Tuesday, March 30, 2021 | 1 |  |  |  |